## Tabelle1
Task	Assigned to	Period (days)	Success Probability	Expected increase of return	Rating	Actual required time	Actual increase in return
Weighted likelihood maximization in CL-model, depending on outer variables: / It is an old idea to cluster the races after the outer variables (like obstacle, going, season…). However, the clusters become too small very quickly and we overfit. What if we introduce a soft clustering and weigh the CL-model fitting according to the weights of the clusters? For example, it may be reasonable to improve the prediction of the flat races more than hurde races.		4	12%	25%	7,50
Add PCA to fit-slices where the market prices are already part of step 1. This way, regularization introduces by PCA my be more effective.		1	10%	5%	5,00
Boosting with rules from the internet, like is suggested by Shapire in this article: / http://cseweb.ucsd.edu/~yfreund/papers/IntroToBoosting.pdf / Try to pick rules that bring orthogonal value to the present CL-model. / Lists with rules: / http://www.runhorse.com/how_to_pick_winners.htm / http://www.runhorse.com/how_to_pick_winners_2.htm / http://www.telegraph.co.uk/sport/horseracing/grand-national/11527720/Grand-National-eight-rules-to-pick-the-winner.html / http://www.wikihow.com/Win-at-Horse-Racing / Look for more.		10	20%	20%	4,00
CL-Boosting: / The direct application of boosting methods doesn‘t work for the CL-model since the combination of several linear models is a linear model itself. Find a non-linear combination of CL-models such that the same factors can be reused to predict the residuals better.		10	12%	25%	3,00
Mixed Effects Models for speed estimation. / Add runner_id and other Ids in order to estimate the speed better.		5	10%	10%	2,00
Weighted likelihood maximization in CL-model, depending on how long ago a race was. Assign lower weights to races that were long ago.		4	5%	10%	1,25
Likelihood-guided PCA: / Usually, PCA throws away components that don‘t contribute much to the variance of the data. However, those components can be orthogonal to the market prices and therefore very valuable. Can we construct some sort of „likelihood-guided“ PCA that looks predominantly for orthogonal compontents?		10	12%	10%	1,20
Research how to detect the presence of insider information. When detected, stop betting.		5	5%	10%	1,00
Multiple-targets missing value regression during preprocessing: / The algorithm starts with a linear regression of a single target and then uses the coefficients to compute all other missing ones. Replace the single-target regression with the more proper multiple target regression.		7	5%	10%	0,71
Second order probabilities: / What if we can provide each probability with a confidence interval, that tells us how well we know the probability? How do our predictions change?		20	5%	10%	0,25